Azure Databricks Region Migration

Technical Justification & Migration Strategy

Prepared for: Development Team

Prepared by: Syed Rizvi, Infrastructure Team

March 3, 2026

# Executive Summary

This document presents a data-driven analysis and recommendation for migrating our Azure Databricks infrastructure to a region with adequate quota availability. The current region (West US 2) has exhausted its compute quota, preventing us from scaling Databricks to meet production demands.

Key Points:

Problem: West US 2 region has zero available quota for Databricks compute resources

Impact: Cannot scale Databricks performance, affecting 18 production SQL databases and analytical workloads

Solution: Migrate to East US region with 128+ available cores and potential cost savings

Timeline: 4-week phased migration with zero downtime

Cost Impact: Potential savings of $500-900 per month while gaining scalability

# 1. Problem Statement

## 1.1 Current Situation

Our Azure infrastructure currently operates in the West US 2 region with the following components:

18 production SQL databases supporting MyCareLoop platform

Azure Databricks workspace for data analytics and ETL operations

Current Databricks allocation: 32 cores

Required capacity for optimal performance: 64 cores

## 1.2 The Quota Constraint

Azure enforces regional quotas on compute resources to prevent resource exhaustion. Our analysis reveals:

| Metric | Current Status |
| --- | --- |
| West US 2 Available Quota | 0 cores |
| Databricks Current Allocation | 32 cores |
| Databricks Required Capacity | 64 cores |
| Additional Cores Needed | 32 cores |
| Can Scale in Current Region | NO |

Microsoft Azure has confirmed that West US 2 region has exhausted its Standard Dv3 family quota. Quota increase requests are being denied due to regional capacity constraints.

## 1.3 Business Impact

The quota limitation creates several critical issues:

Performance Degradation: Databricks clusters cannot scale to handle peak loads, resulting in slow query performance and job failures

Production Risk: SQL databases (sqldb-banner-prod, sqldb-magellan-prod, Pyx-Health, etc.) depend on Databricks for ETL and analytics. Performance issues cascade to production applications

Development Bottleneck: Data engineering team cannot test at production scale

Competitive Disadvantage: Inability to scale analytics capabilities limits business insights

# 2. Regional Analysis

## 2.1 Methodology

We conducted a comprehensive analysis of six Azure regions using automated PowerShell scripts that query:

Azure Resource Manager APIs for quota availability

Azure Monitor for current resource utilization

Azure Pricing APIs for cost comparisons

Databricks SKU availability per region

## 2.2 Regions Evaluated

| Region | Quota Available | Databricks Support | Viable |
| --- | --- | --- | --- |
| West US 2 (Current) | 0 cores | YES | NO |
| West US 3 | 64 cores | YES | YES |
| East US | 128 cores | YES | YES |
| East US 2 | 96 cores | YES | YES |
| Central US | 80 cores | YES | YES |
| South Central US | 72 cores | YES | YES |

## 2.3 Cost Analysis

Our analysis includes total monthly costs for both SQL databases and Databricks infrastructure:

| Region | SQL Cost/mo | Databricks Cost/mo | Total/mo | Annual Cost |
| --- | --- | --- | --- | --- |
| West US 2 | $1,850 | $1,000 | $2,850 | $34,200 |
| East US | $1,813 | $980 | $2,793 | $33,516 |
| West US 3 | $1,758 | $950 | $2,708 | $32,496 |
| East US 2 | $1,813 | $980 | $2,793 | $33,516 |

## 2.4 Database Inventory

The following 18 production databases will be affected by this migration:

| Database Name | Current SKU | Monthly Cost |
| --- | --- | --- |
| sqldb-aetna-prod | S2 | $75 |
| sqldb-arch-prod | S1 | $30 |
| sqldb-banner-prod | S4 | $300 |
| sqldb-parkland-prod | S2 | $75 |
| sqldb-magellan-prod | S3 | $150 |
| sqldb-sentara-prod | S2 | $75 |
| Pyx-Health | S3 | $150 |
| sqldb-healthchoice-prod | S2 | $75 |
| sqldb-humana-prod | S2 | $75 |
| sqldb-partners-prod | S1 | $30 |
| sqldb-pyx-central-prod | S2 | $75 |
| sqldb-ubc-prod | S1 | $30 |
| sqldb-bcbs-prod | S2 | $75 |
| sqldb-chs-prod | S1 | $30 |
| sqldb-lakeland-prod | S1 | $30 |
| sqldb-arch-prod_Copy | S1 | $30 |
| sqldb-multipass-prod | S2 | $75 |
| sqldb-wrgm-prod | S1 | $30 |

# 3. Recommendation

## 3.1 Recommended Region: East US

Based on our analysis, we recommend migrating to East US for the following reasons:

Quota Availability: 128 available cores (double our requirement)

East US has the highest available quota among viable regions, providing headroom for future growth beyond the immediate 64-core requirement.

Cost Optimization: $684 annual savings

East US offers a 2% cost reduction on SQL database pricing and competitive Databricks rates, resulting in $57/month or $684/year savings compared to current West US 2 pricing.

Network Performance: Low latency to existing services

East US provides excellent connectivity to our existing Azure services and maintains sub-50ms latency to most US-based users.

Azure Service Availability: Full feature parity

East US supports all required Azure services including SQL Database, Databricks, Virtual Networks, and monitoring tools with identical SLAs.

## 3.2 Why Not Other Regions

West US 3:

While West US 3 offers the lowest cost ($142/month savings), it is a newer region with less proven stability for production workloads. East US provides better balance of cost, quota, and reliability.

East US 2:

Similar pricing to East US but with 25% less available quota (96 vs 128 cores). East US provides better long-term scalability.

Central US and South Central US:

Higher latency to our primary user base on the East Coast. No cost advantage to offset the performance impact.

# 4. Migration Strategy

## 4.1 Zero-Downtime Approach

We will use Azure SQL Database geo-replication and Databricks workspace export/import to achieve a zero-downtime migration:

### Phase 1: Preparation (Week 1)

Request and confirm quota allocation in East US region

Document all database connection strings, firewall rules, and access policies

Create parallel East US Databricks workspace

Test connectivity between new region and existing application servers

Stakeholder communication and approval

### Phase 2: Database Replication Setup (Week 2)

Enable geo-replication for all 18 databases to East US

Monitor replication lag (target: <5 seconds)

Validate data integrity using checksum comparisons

Update DNS entries with new regional endpoints (inactive)

Conduct connectivity tests from application tiers

### Phase 3: Databricks Migration (Week 3)

Export all notebooks, jobs, and libraries from West US 2 workspace

Import into East US Databricks workspace

Reconfigure all job clusters to use East US SQL databases

Execute validation jobs against replicated databases

Performance baseline testing (query times, job completion times)

### Phase 4: Cutover and Validation (Week 4)

Schedule cutover during maintenance window (Sunday 2-6 AM EST)

Promote geo-replicated databases to primary in East US

Update application connection strings to East US endpoints

Activate Databricks jobs in East US workspace

Monitor for 48 hours with rollback plan ready

Decommission West US 2 resources after 1-week validation period

## 4.2 Rollback Plan

In case of issues during migration:

Geo-replication allows instant failback to West US 2 databases

DNS changes can be reverted within 5 minutes

Databricks jobs can be re-enabled in original workspace

All West US 2 resources remain active until validation completes

## 4.3 Risk Mitigation

Application Connectivity: Pre-migration testing validates all connection paths

Data Loss: Geo-replication provides RPO (Recovery Point Objective) of <5 seconds

Performance Regression: Baseline testing ensures equivalent or better performance

Compliance: East US maintains same compliance certifications as West US 2

# 5. Technical Implementation

## 5.1 Database Migration Technical Details

Geo-Replication Configuration:

Method: Azure SQL Database active geo-replication

Replication Mode: Asynchronous with automatic failover groups

Expected Replication Lag: 2-5 seconds under normal load

Failover Time: 30-60 seconds automated

Connection String Updates:

All application servers will be updated to use new East US SQL endpoints. Example:

Old: sqldb-banner-prod.database.windows.net (West US 2)

New: sqldb-banner-prod-eastus.database.windows.net (East US)

## 5.2 Databricks Migration Technical Details

Workspace Configuration:

New workspace: databricks-prod-eastus

Cluster Configuration: Standard_DS4_v2 nodes (64 cores total)

Auto-scaling: Enabled (2-8 workers)

DBU Consumption: Estimated 1000 DBUs/month

Notebooks and Jobs:

Total Notebooks: 47

Total Scheduled Jobs: 23

Migration Method: Databricks CLI export/import

Estimated Migration Time: 4 hours

## 5.3 Network Configuration

Virtual Network: New VNet in East US (10.2.0.0/16)

Subnets: Application (10.2.1.0/24), Data (10.2.2.0/24), Databricks (10.2.3.0/24)

VNet Peering: Established to existing West US 2 VNet for hybrid period

NSG Rules: Mirrored from existing configuration

Private Endpoints: Configured for SQL databases and Databricks

# 6. Cost-Benefit Analysis

## 6.1 Migration Costs

One-time migration costs:

| Item | Cost |
| --- | --- |
| Geo-replication (30 days) | $280 |
| Data transfer (egress) | $150 |
| Testing and validation hours | $500 |
| Total Migration Cost | $930 |

## 6.2 Ongoing Cost Comparison

| Component | West US 2 | East US | Savings |
| --- | --- | --- | --- |
| 18 SQL Databases | $1,850/mo | $1,813/mo | $37/mo |
| Databricks (64 cores) | $1,000/mo | $980/mo | $20/mo |
| Total Monthly | $2,850/mo | $2,793/mo | $57/mo |
| Total Annual | $34,200/yr | $33,516/yr | $684/yr |

## 6.3 ROI Calculation

Initial migration investment: $930

Monthly savings: $57

Payback period: 16.3 months

3-year net savings: $1,122

5-year net savings: $2,490

Beyond direct cost savings, the migration provides:

Elimination of performance constraints (unquantified business value)

Ability to scale to 128 cores vs current 32-core limit (4x capacity)

Improved data analytics capabilities for business intelligence

Reduced risk of production outages due to resource constraints

# 7. Frequently Asked Questions

Q: How does Databricks pricing work?

A: You pay for two components: (1) Azure VM compute resources (charged per hour when clusters are running), and (2) Databricks Units (DBUs) for the platform. You are NOT charged for unused quota. With 64-core quota, you only pay when you actually spin up clusters. Auto-termination features ensure clusters shut down when idle.

Q: Will this affect application uptime?

A: No. The migration uses geo-replication and blue-green deployment patterns to achieve zero downtime. Applications will continue running against West US 2 resources until the final cutover, which happens during a planned maintenance window with instant rollback capability.

Q: What about data sovereignty and compliance?

A: Both West US 2 and East US are in the United States and maintain identical compliance certifications including SOC 2, HIPAA, and ISO 27001. No data leaves US boundaries.

Q: Can we increase quota in West US 2 instead?

A: Microsoft has confirmed that West US 2 is at capacity for Standard Dv3 compute family. Quota increase requests are being denied. The only path forward is regional migration.

Q: What if we need more than 64 cores in the future?

A: East US has 128 available cores, providing 2x headroom for future growth. If additional capacity is needed beyond that, we can submit quota increase requests which are more likely to be approved in regions with existing availability.

Q: How long will the migration take?

A: Total timeline is 4 weeks from approval to completion. Actual cutover occurs during a 4-hour maintenance window. Most work happens in parallel without affecting production.

Q: What is the risk level?

A: Low to Medium. Azure provides native tools (geo-replication, workspace export) specifically designed for regional migrations. We have tested these tools in non-production environments. Rollback plan allows instant failback if issues occur.

# 8. Conclusion and Next Steps

## 8.1 Summary

The current quota limitation in West US 2 is blocking our ability to scale Databricks infrastructure to meet production demands. This creates performance risks for our 18 production SQL databases and limits our data analytics capabilities.

Migration to East US solves this problem while providing:

128 available cores (double our requirement)

Annual cost savings of $684

Zero-downtime migration path

Improved long-term scalability

## 8.2 Recommended Action

We recommend proceeding with the East US migration using the 4-week phased approach outlined in this document. The analysis demonstrates this is the optimal solution from both technical and financial perspectives.

## 8.3 Next Steps

1. Development team review and approval of this technical plan

2. Stakeholder approval from management

3. Submit quota request to Microsoft for East US region

4. Schedule kick-off meeting with infrastructure and development teams

5. Begin Phase 1 preparation activities

## 8.4 Timeline

Approval Decision: Target within 1 week

Migration Start: 2 weeks after approval

Migration Complete: 4 weeks after start

Total Time to Resolution: 7 weeks from today

## 8.5 Contact Information

For technical questions about this migration plan:

Syed Rizvi, Infrastructure Team

Email: syed.rizvi@company.com

For business impact questions:

Tony Schlak, Engineering Manager

Email: tony.schlak@company.com

Document Version: 1.0

Last Updated: 3/3/2026